AVC Plan
Team 2 Members
Chris Parry: Team Leader, Network
     Github User : parryman
Jakob Kleparek:Lead Hardware Github username Jkleparek
Siddha Ganesan :Hardware, Proof Reading
     Github Username: ganesasidd
Charlie Cameron:Lead Software Github User: Charlie1510
Kristen Tait:Software- Quadrant 4 Github Username: taitkris
Repository
https://github.com/ganesasidd/AVC_Team2_2016
Team Agreement
By signing below, all team members are acknowledging that they have read and committed to
their part in the AVC. They acknowledge that they will attempt to complete the tasks agreed on
by the group each week and document this on the team Github account. They acknowledge that
failure to meet these goals can result in the team recommending any member receives a lesser
grade for their AVC report. In the event that a team member is unable to complete their task due
to circumstances beyond their control (i.e. sickness, bereavement etc) that they will inform the
team at the earliest possible time. Finally, the team acknowledges that a member going a week
without contact with other team members (except when discussed with the team in advance) will
constitute the member in question being considered AWOL. In this instance the team agrees to
inform the ENGR101 course coordinator immediately. The penalty this for this can range from a
reduction in the nal grade to immediate failure of the AVC (and thus the ENGR101 course).
Should the team unanimously agree that a member (or members) have failed to contribute to
the AVC sufficiently for other reasons, on the day of robot testing the team will be given the
opportunity to anonymously vote for a team member to receive 0% for the robot part of the AVC.
Should the team choose this option they MUST
be able to show that the member in question
had been assigned tasks that they failed to
complete and that the team had given them
an opportunity to make up for past mistakes.
Signed by all team members:
(Printed Name)/ (Signature)

---
AVC Task Plan
Week
Date
Items Due
Confliction
Team Objectives
Tasks
Commitments
1
18 April
AVC Plan Due
PHYS122
Goals:
Complete AVC
Test(Fri)
Write working code for
plan
PHYS114
straight line
Test(Thu)
Design chassis and
body
Decide on Wheels
Set up Github account
 Brainstorm and
design Robot
2
25th
Meet and plan for
April
following week
 Update GitHub
 repository
3
2nd May
Quadrant 1 complete
4
9th May
COMP102 Test
Quadrant 2 complete
Write Results
and Discussion
Sections
5
16th
Progress
ENGR121 Test
Quadrant 3 complete
Update sections
May
Report Due
with new results
6
23rd
Jakob having
Quadrant 4 complete
Update sections
May
surgery 24th
with new results
7
30th
Robot Due
ENGR101 Test
 Demonstrate Robot to
 customer
Revise sections
May
based on
feedback
 Finals Due
8
6th June
Write
  Compete in finals
Conclusion and
Abstract
sections
9
13th
Final Report
June
Due